## Kushal
Spring Boot | Task | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
Get Schedule List | code for service | 30 mins | 30 mins | Completed | Completed
| code in controller | 30 mins | 1 hour | Completed
| test functionality with postman | 15minutes | 15 mins | Completed
Completed
Completed
Add Store | test functionality with postman | 15minutes | 5 mins | Completed
| code for service | 30 mins | 30 mins | Completed
| code in controller | 30 mins | 1 hour | Completed
Completed
| validation/error handling | 1 hour | 1 hour | Completed
Completed
Update Store | test functionality with postman | 15 minutes | 5 mins | Completed
| code for service | 30 mins | 30 mins | Completed
| code in controller | 30 mins | 1 hour | Completed
Completed
| validation/error handling | 30 minutes | 30 minutes | Completed
Completed
Remove Store | test functionality with postman | 15 minutes | 10 minutes | Completed
| code for service | 30 mins | 30 mins | Completed
| code in controller | 30 mins | 1 hour | Completed
| validation/error handling | 30 minutes | 5 minutes | Completed
Add Pizza | test functionality with postman | 15 mins | 15 mins | Completed
| code for service | 30 mins | 30 mins | Completed
| code in controller | 30 mins | 1 hour | Completed
| validation | 2 hours | 2 hour | Completed
Update Pizza | test functionality with postman | 15 mins | 15 mins | Completed
| code for service | 30 mins | 30 mins | Completed
| code in controller | 30 mins | 1 hour | Completed
Remove Pizza | test functionality with postman | 15 mins | 15 mins | Completed
| code for service | 30 mins | 30 mins | Completed
| code in controller | 30 mins | 1 hour | Completed
| validation/error handling | 30 minutes | 1 hour | Completed
Audit Trail | Backend | 45 minutes | 45 minutes | Completed
Loggers | Controller and Service | 2 hours | 1.5 hours | Completed
Comments | Backend | On the go |  | Completed
Angular | Task | Estimated hours/Time | Actual Time Taken
Add Store | test functionality with postman | 15minutes | 15 mins | Completed
| addStore.ts | 3 hour | 6 hour | Completed
| addStore.html | 1 hour |  | Completed
| code for service | 1 hour |  | Completed
| validation/error handling | 1 hour | 1 hour | Completed
Update Store | test functionality with postman | 15 minutes | 5 mins | Completed
| updateStore.ts | 30 minutes | 1 hour | Completed
| updateStore.html | 30 minutes | 30 minutes | Completed
| code for service | 30 minutes | 30 minutes | Completed
| validation/error handling | 30 minutes | 30 minutes | Completed
Completed
Remove Store | test functionality with postman | 15 minutes | 10 minutes | Completed
| removeStore.html | 30 minutes | 20 minutes | Completed
| removeStore.ts | 30 minutes | 30 minutes | Completed
| code for service | 30 minutes | 15 mins | Completed
| validation/error handling | 30 minutes | 5 minutes | Completed
Integrating JWT | Test rest with postman | 1 hour | 2 hour | Completed
| Implement basic hardcoded security for testing | 1 hour | 30 minutes | Completed
| login.ts | 30 minutes | 30 minutes | Completed
| error pages . html | 30 mins | 20 minutes | Completed
| errorpages.ts | 15 minutes | 15minutes | Completed
| basic Auth service | 15 minutes | 15minutes | Completed
| login service in angular | 1 hour | 2 hour | Completed
Add Pizza | test functionality with postman | 15 mins | 15 mins | Completed
| addpizza.ts | 1 hour | 1 hour | Completed
| addpizza.html | 1 hour | 1 hour | Completed
| code for service | 1 hour | 1 hour | Completed
| validation | 2 hours | 2 hour | Completed
Delete Pizza | test functionality with postman | 15 mins | 15 mins | Completed
| deletepizza.ts | 2 hours | 2 hours | Completed
| deletepizza.html | 1 hour | 1 hour | Completed
| code for service | 1 hour | 1 hour | Completed
Make Cart | test functionality with postman | 15 minutes | 15 minutes | Completed
| makecart.ts | 30 minutes | 1 hour | Completed
| makecart.html | 30 minutes | 30 minutes | Completed
| code for service | 30 minutes | 30 minutes | Completed
| validation/error handling | 30 minutes | 1 hour | Completed
UI Designing | Reading Templates | 2 hour | 6 hour | Completed
| Home page | 2 hour | 2 hour | Completed
| Userhome | 1 hour | 45 minutes | Completed
| AdminHome | 1 hour | 1 hour | Completed
| Implementing more deisgns | 1 hour | 1 hour | Completed
Update Cart | test functionality with postman | 15 minutes | 15 minutes | Pending
| updatecart.ts | 30 minutes | 1 hour | Pending
| updatecart.html | 30 minutes | 30 minutes | Pending
| code for service | 30 minutes | 30 minutes | Pending
| validation/error handling | 30 minutes | 1 hour | Pending

## Task
Angular | Each Task contains the following sub task/module wise work:
Test Rest functionality using Postman
code component.ts
code html file of the component (basic UI)
code service layer
comments in angular
update UI as per the chosen template